## Start Here
This Excel template is inspired by our effective Goal Tracker web app, designed to help you set, monitor, and achieve your goals efficiently. Use this template to stay organized, track progress, and reach your targets with ease. Ready for the next step? Upgrade to Tadabase and turn this template into a fully automated, interactive database with custom workflows, user roles, and real-time updates.
What’s Inside? Goals: Record and track goals, including descriptions, owners, deadlines, and progress percentages. Milestones: Break goals into milestones with due dates, statuses, and progress tracking. Tasks: Assign, prioritize, and monitor tasks linked to milestones for better goal management. Team Members: Maintain team member details, including roles, contact information, and availability. Reports: Generate summaries on goal progress, milestone statuses, and overall achievements.
Build it Easily with Tadabase

## Goals
GOALS
Goal ID | Goal Name | Description | Owner | Start Date | Target Date | Status | Progress (%)
G001 | Increase Website Traffic | Boost monthly traffic by 30% | Alice Johnson | 2025-01-01 | 2025-06-30 | In Progress | 45
G002 | Develop New Product | Launch a new product line by Q4 | John Smith | 2025-02-01 | 2025-12-31 | Not Started | 0
Build it Easily with Tadabase

## Milestones
MILESTONES
Milestone ID | Goal ID | Milestone Name | Due Date | Status | Progress (%)
M001 | G001 | Conduct SEO Audit | 2025-02-15 | Completed | 100
M002 | G001 | Create Content Calendar | 2025-03-31 | In Progress | 20
M003 | G002 | Complete Market Research | 2025-06-30 | Not Started | 0
Build it Easily with Tadabase

## Tasks
TASKS
Task ID | Milestone ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority
T001 | M001 | Analyze Competitors | Sophia Brown | 2025-01-10 | 2025-02-10 | Completed | High
T002 | M002 | Draft Blog Topics | Michael Lee | 2025-02-20 | 2025-03-10 | In Progress | Medium
T003 | M003 | Gather Customer Feedback | Emily Davis | 2025-05-01 | 2025-06-15 | Not Started | Low
Build it Easily with Tadabase

## Team Members
TEAMS MEMBERS
Member ID | Name | Role | Email | Phone | Availability
TM001 | Alice Johnson | Marketing Lead | alice.johnson@example.com | 555-123-4567 | Available
TM002 | John Smith | Product Manager | john.smith@example.com | 555-987-6543 | Available
TM003 | Sophia Brown | SEO Specialist | sophia.brown@example.com | 555-654-3210 | Unavailable
Build it Easily with Tadabase

## Reports
REPORTS
Report ID | Type | Generated By | Generated On | Details
R001 | Goal Progress Report | Admin | 2025-03-01 | Summary of all goals and their progress.
R002 | Milestone Status Report | Admin | 2025-03-15 | Detailed status of milestones across all goals.
Build it Easily with Tadabase